MOONLIGHT COFFEE

Store #2 — Seongsu-dong, Seoul

Interior Design Proposal

Floor Plan  ·  Design Concept  ·  Space Plan  ·  Schedule

Customer:  Moonlight Coffee (Store #2, Seongsu-dong, Seoul)

Prepared for:  Soyul Han, Operations Team

Date:  October 28, 2026

Version:  Draft for customer review

# 1. Design Concept

Store #2 carries over the warm wood tone that defines Store #1. The concept wraps the 12 m × 9 m (approximately 108 m²) space in natural wood and soft, warm light, creating a calm, inviting atmosphere that glows from morning through the late night — the "Moonlight" mood the brand is named for. The hall provides seating for about 40 customers, while the back-of-house rooms (bean storage, staff lounge, restroom) are arranged compactly so the front-of-house feels open and uncluttered.

Mood

- Warm, calm and inviting — a quiet "Moonlight" glow that works for both day and late-night hours

- Continuity with Store #1, so regulars feel the same warmth at the new location

- Open hall with clear sightlines to the bar; back-of-house rooms tucked quietly away

Materials

- Warm wood veneer (oak / walnut tone) on the flooring, wall panels and bar front

- Natural stone countertop at the order and coffee bar

- Brass accents with matte-black hardware

- Soft warm-white lighting (approximately 2700 K) for the "Moonlight" ambience

- Warm neutral wall palette (cream, taupe, walnut brown)

# 2. Space Plan

Total floor area is approximately 108 m² (12 m × 9 m). The hall is allocated about 40 customer seats as requested.

| Room | Area | Use |
| --- | --- | --- |
| Hall | 56 m² | Customer seating |
| Bar | 16 m² | Order and coffee bar |
| Storage | 12 m² | Bean storage |
| Staff Lounge | 12 m² | Staff lounge |
| Restroom | 12 m² | Restroom |
| Total | 108 m² | — |

# 3. Floor Plan

Figure 1.  Store #2 floor plan (12 m × 9 m, total approx. 108 m²).

# 4. Schedule and Next Steps

Target: opening of Store #2 in March 2027, as requested. Indicative schedule below.

| Phase | Period | Description |
| --- | --- | --- |
| 1. Proposal & quote review | Oct 28 – Nov 6, 2026 | Customer reviews the proposal and quote; scope and budget confirmed |
| 2. Detailed design | Nov 9 – Dec 18, 2026 | Final floor plan, material and fixture selection, 3D renders for approval |
| 3. Procurement | Dec 2026 – Jan 2027 | Order custom furniture, bar counter and building materials |
| 4. Construction | Jan 5 – Feb 26, 2027 | Partitioning, wood finishing, electrical and lighting, furniture installation |
| 5. Handover & opening | Early Mar 2027 | Punch list, final cleaning, equipment installation, opening |

Next steps

- Review and approve the proposal and quote by Friday, November 6, 2026.

- Confirm the material palette (wood species, stone, lighting tone) and budget range.

- Schedule a site survey of the Seongsu-dong premises and a design-development kickoff meeting.

- After approval, we will issue detailed drawings, 3D renders and the full construction schedule.